## ongoing
GITTO COSTRUZIONI GENERALI NIGERIA LTD
LIST OF ONGOING PROJECTS | [11 empty] | 2024-05-22
No. | PROJECT NAME | SCOPE OF WORK | CLIENT | LOCATION | Date of Award Original Contract | Compl. Date | Original Contract Amount NGN | Current Augmented Contract Amount NGN | Works Done Amount NGN | Oustanding Works to completion NGN | % Compl. | Remarks | USD/NGN | NGN/USD | Original Contract Amount USD | Current Augmented Contract Amount USD | Works Done Amount USD
1 | Dualization of East-West Road Section IV Eket-Oron - Contract No. 5883 | Construction of 51-km double lane single carriageway road with 6-no. bridges with a total length of 550m. | Federal Republic of Nigeria - Ministry of Works & Housing | Akwa Ibom State Nigeria | sep-06 | aug-25 | 26000000000 | 64347840000 | 37328529000 | 27019311000 | 58% | on-going | 0.007797 | 128.26 | 202722000 | 501720108.48 | 291050540.613
2 | Dualization of Abuja-Abaji- Lokoja Highways Section IV: Koton-Karfe-Lokoja Road | construction of a double lane single carriageway of 49.43km long with supporting lined drains and rehabilitation of the existing carriageway with construction of 7-No Bridges. | Federal Republic of Nigeria - Ministry of Works Highways Dep. | Kogi State Nigeria | sep-06 |  | 11987550000 | 34092748000 | 25967293000 | 8125455000 | 76% | on-going with possible augmentation | 0.007797 | 128.26 | 93466927.35 | 265821156.156 | 202466983.521
3 | Completion of the Rehabilitation of Nassarawa- Loko Road | Rehabilitation of existing single carriageway with associated drains and culverts. | Federal Republic of Nigeria - Ministry of Works Highways Dep. | Nassarawa State Nigeria | jun-15 |  | 15190821000 | 8870451000 | 8326411000 | 544040000 | 94% | substantially completed | 0.005026 | 198.9749 | 76349066.346 | 44582886.726 | 41848541.686
4 | Construction of Dual Dual Carriageway Eket By Pass, Eket- Oron Road Section IV ID752 | Construction of 9,75 km of Dual Carriageway from the Junction after the Eket Bridge on the existing East West Road Dualization alignment. | Federal Republic of Nigeria - Ministry of Niger Delta | Akwa Ibom State Nigeria | may-19 | mar-26 | 16161269000 | 76838686000 | 10118214000 | 66720472000 | 13% | on-going | 0.002778 | 359.9967 | 44896005.282 | 213457869.708 | 28108398.492
5 | Rehabilitation of National Christian Centre | Rehabilitation of the Roof of the existing Christian Church of Building | Federal Capital Development Authority (Abuja) | FCT Abuja | feb-21 |  | 496609000 | 496609000 | 461594000 | 35015000 | 93% | substantially completed | 0.002624 | 381.1529 | 1303102.016 | 1303102.016 | 1211222.656
6 | Construction of Omelema- Agada Road Phase I | Construction of 6.1km long double lane single carriageway connecting Omelema and Agada communities. | Federal Republic Of Nigeria - Ministry of Niger Delta | River State Nigeria | Dec-10 |  | 6219732000 | 6219732000 | 894775000 | 5324957000 | 14% | suspended | 0.006515 | 153.5004 | 40521553.98 | 40521553.98 | 5829459.125
7 | Osun Liason Office | Six storey office complex for the State with external and basement parking and driveway | Osun State | Osun State Nigeria | Aug-05 |  | 1335300000 | 3944910000 | 2368102000 | 1576808000 | 60% | suspended | 0.007326 | 136.5 | 9782407.8 | 28900410.66 | 17348715.252
8 | Akwa Ibom International Airport Phase I | International Standard Runway of 3.6km & 60m wide and an interim terminal Apron and MRO Apron. | Government of Akwa Ibom State Nigeria | Akwa Ibom State Nigeria | jun-05 |  | 10329277000 | 10329277000 | 9933052000 | 396225000 | 96% | substantially completed suspended | 0.007477 | 133.75 | 77232004.129 | 77232004.129 | 74269429.804
9 | Construction of 20th Anniversary Specialist Hospital, Uyo | Main Building housing supported by a Service Building and ancillary building. | Federal Republic of Nigeria - Government of Akwa Ibom State | Akwa Ibom State Nigeria | may-09 |  | 11976453000 | 14845129000 | 13513732000 | 1331397000 | 91% | substantially completed suspended | 0.006791 | 147.25 | 81332092.323 | 100813271.039 | 91771754.012
10 | Construction of Itigidi Bridge & Approach Roads | Construction of Multiple Span Bridge and 26-km double lane single carriageway with a spur road of about 1.5km. | Federal Republic of Nigeria - Ministry of Works | Cross River State Nigeria | mar-03 |  | 5245064000 | 7415572000 | 6544383000 | 871189000 | 88% | substantially completed suspended | 0.007131 | 129.35 | 37402551.384 | 52880443.932 | 46667995.173
| GRAND TOTAL | [5 empty] | 104942075000 | 227400954000 | 115456085000 | 111944869000 | 51%

## completed
GITTO COSTRUZIONI GENERALI NIGERIA LTD
LIST OF COMPLETED/SUBSTANTIALLY COMPLETED PROJECTS AND TOP CUSTOMERS | [8 empty] | 2024-05-31
Cat. | No. | PROJECT NAME | CLIENT | LOCATION | Award contract Date | Completion Date | Original Contract Amount NGN | Revised Contract Amount NGN | Remarks | USD/NGN | NGN/USD | Original Contract Amount USD | Revised Contract Amount USD | USD/TL | Original Contract Amount TL | Revised Contract Amount TL | İLK SÖZLEŞME GÜNCEL DEĞERİ TL | SÖZLEŞME SONU GÜNCEL DEĞERİ TL
AIRPORTS | 1 | Akwa Ibom International Airport Phase I | Government of Akwa Ibom State | Akwa Ibom State Nigeria | 2005 | 2010 | 11970413593 | 13030865474 | completed | 0.007501 | 133.3 | 89790072.3611 | 97744521.9205 | 1.3368 | 120031368.7323 | 130664876.9033
ROADS/HIGHWAYS/INFRASTRUCTUR ES | 2 | Dualization of Abak Road Uyo | Akwa Ibom State Government | Akwa Ibom State Nigeria | 2004 | 2010 | 3574300488 | 3918133083 | completed | 0.007528 | 132.847 | 26907334.0737 | 29495705.8488
| 3 | Dualization of Oron Road (Section II) | Government of Akwa Ibom State - Ministry of Works & Transport | Akwa Ibom State Nigeria | 2007 | 2010 | 10385769781 | 13916931507 | completed | 0.007884 | 126.845 | 81881408.9534 | 109721088.0012
| 4 | Construction of Itigidi Bridge & Approach Roads | Federal Republic of Nigeria - Ministry of Works | Cross River State Nigeria | 2003 | 2013 | 5245063676 | 7415571827 | substantially completed | 0.007743 | 129.15 | 40612528.0433 | 57418772.6565
| 5 | Rehabilitation of Nasarawa Loko Road | Federal Republic of Nigeria - Ministry of Works | Nassarawa State | 2006 | 2023 | 15190821000 | 8870451000 | substantially completed | 0.007827 | 127.75 | 118898555.967 | 69429019.977
BUILDINGS | 6 | Completion of Shehu Shagari Presidential Complex | Federal Capital Development Authority | Abuja FCT State Nigeria | 2006 | 2010 | 2650000000 | 3228575454 | completed | 0.007827 | 127.75 | 20741550 | 25270060.0785
| 7 | Construction of the National Ecumenical Centre | National Christian Association | Abuja FCT State Nigeria | 2005 | 2008 | 2600000000 | 2600000000 | completed | 0.007501 | 133.3 | 19502600 | 19502600
| 8 | Presidential Library & Hotel | OOPL Foundation | Abeokuta Nigeria | 2005 | 2009 | 4936151037 | 4936151037 | completed | 0.007501 | 133.3 | 37026068.9285 | 37026068.9285
| 9 | Construction of 20th Anniversary Specialist Hospital, Uyo | Federal Republic of Nigeria - Government of Akwa Ibom State | Akwa Ibom State Nigeria | 2009 | 2014 | 11976453324 | 14845128288 | substantially completed | 0.006773 | 147.65 | 81116518.3635 | 100546053.8946
| 10 | Central Bank of Nigeria Yenagoa Branch Prototype Building | Central Bank of Nigeria | Bayelsa State Nigeria | 2010 | 2019 | 10809064515 | 14249429652 | completed | 0.00668 | 149.7 | 72204550.9602 | 95186190.0754
|  | GRAND TOTAL |  |  |  |  | 79338037414 | 87011237322